## Sheet1
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  |  |  | Repo | Find data sources | GitHub Process | Time Dim | Pre-DB load | Data Ingest | Data Store | Manage collaboration | EDA | Analysis | Visual | Report |  | Tasks
Week | Day | Date | Weekday | 1: Done | 1 | Create time dimension in Python
1 | 1 | 2020-09-28 | Monday | [12 empty] | 2 | Produce Report | bar: 2 to 4
1 | 2 | 2020-09-29 | Tuesday | [12 empty] | 3 | Analysis: Visualisations | bar: 2 to 4
1 | 3 | 2020-09-30 | Wednesday | [12 empty] | 4 | Analysis: Perform Data and Inferential Analysis | bar: 2 to 4
1 | 4 | 2020-10-01 | Thursday | [12 empty] | 5 | Analysis: Perform EDA | bar: 2 to 4
1 | 5 | 2020-10-02 | Friday | [12 empty] | 6 | Design and Develop Data Storage | bar: 2 to 4
1 | 6 | 2020-10-03 | Saturday | [12 empty] | 7 | Design and Develop Data Ingestion | bar: 2; 4
1 | 7 | 2020-10-04 | Sunday | [12 empty] | 8 | Manage team collaboration | bar: 2; 4
2 | 8 | 2020-10-05 | Monday | [12 empty] | 9 | Design GitHub process for committing/branching/merging code | bar: 4 to 5
2 | 9 | 2020-10-06 | Tuesday | [12 empty] | 10 | Create GitHub Repo for group and add group members. | bar: 5
2 | 10 | 2020-10-07 | Wednesday | [12 empty] | 11 | Finalise finding data sources | bar: 6 to 7
2 | 11 | 2020-10-08 | Thursday | [12 empty] | 12 | Code pre-database load data preparation in Python | bar: 6 to 7; 9 to 10
2 | 12 | 2020-10-09 | Friday | bar: 6 to 7; 9 to 10
2 | 13 | 2020-10-10 | Saturday | bar: 6 to 7; 9 to 10
2 | 14 | 2020-10-11 | Sunday | bar: 6 to 7; 9 to 10
3 | 15 | 2020-10-12 | Monday | bar: 6 to 7; 9 to 10
3 | 16 | 2020-10-13 | Tuesday | bar: 6 to 7; 9 to 11
3 | 17 | 2020-10-14 | Wednesday | bar: 6 to 7; 9 to 11
3 | 18 | 2020-10-15 | Thursday | bar: 6 to 7; 9 to 11
3 | 19 | 2020-10-16 | Friday | bar: 9 to 11
3 | 20 | 2020-10-17 | Saturday | [13 empty] | suggested extra days | bar: 9 to 12
3 | 21 | 2020-10-18 | Sunday | bar: 9 to 12
4 | 22 | 2020-10-19 | Monday | bar: 9 to 12
4 | 23 | 2020-10-20 | Tuesday | bar: 10 to 12
4 | 24 | 2020-10-21 | Wednesday | bar: 10 to 12
4 | 25 | 2020-10-22 | Thursday | bar: 10 to 12
4 | 26 | 2020-10-23 | Friday | bar: 10 to 12
4 | 27 | 2020-10-24 | Saturday | bar: 10 to 12
4 | 28 | 2020-10-25 | Sunday | bar: 12
5 | 29 | 2020-10-26 | Monday | bar: 12
5 | 30 | 2020-10-27 | Tuesday | bar: 12
5 | 31 | 2020-10-28 | Wednesday | bar: 12
5 | 32 | 2020-10-29 | Thursday | bar: 12
5 | 33 | 2020-10-30 | Friday | bar: 12
5 | 34 | 2020-10-31 | Saturday | bar: 12
5 | 35 | 2020-11-01 | Sunday | bar: 12
Owners |  |  |  | Werner | Adrian | Adrian | Adrian | Werner | Werner | Werner | Geoff | Svetlana | Geoff | Adrian | Geoff
[5 empty] | Werner |  | Svetlana | Ankur | Ankur | Ankur | Muhammad | Muhammad | Svetlana | Geoff | Svetlana
[5 empty] | Geoff | [6 empty] | Ankur